## Price Per Sprint - Adjusted Cos
Adjusted Cost Per Sprint Based on Throughput
Sprint ID | Total Weeks | Total Story Points | Total Operating Expenses for Sprint | Expense Per Story Point | Total PBI’s | Expense Per PBI | Throughput (increase / decrease)
11 | 3 | 168 | 81468.3 | 484.9304 | 62 | 1314.0048 | -31.43%
12 | 3 | 301 | 81468.3 | 270.6588 | 68 | 1198.0632 | 22.86%
13 | 2 | 55 | 54312.2 | 987.4945 | 49 | 1108.4122 | -77.55%
14 | 3 | 153 | 81468.3 | 532.4725 | 30 | 2715.61 | -37.55%
15 | 3 | 97 | 81468.3 | 839.8794 | 31 | 2628.0097 | -60.41%
16 | 3 | 63 | 81468.3 | 1293.1476 | 21 | 3879.4429 | -74.29%
17 | 3 | 167 | 81468.3 | 487.8341 | 49 | 1662.6184 | -31.84%
Total Weekly Cost | 27156.1
Maximum Throughput | 245
Adjustment
Reducing four team members lowered resource capacity by 18.75%.
Critical Numbers
Throughput (Story Points or PBI’s in development)
Inventory* (Backlog or prototypes, requirements, design documents, etc. not in backlog - intellectual inventory)
Operating expenses (salaries and equipment)
Lean manufacturing principle demonstrated through this model: Greatest cost improvement comes through increasing throughput and not decreasing operating expenses.
*Source
Agile Scrum: eliminate “intellectual inventory” using Just-In-Time software development
https://pseudosavant.com/blog/2011/01/29/agile-scrum-eliminate-intellectual-inventory-using-just-in-time-software-development/
How to Manage the "7 Wastes" of Agile Software Development
https://www.scrumalliance.org/community/articles/2013/september/how-to-manage-the-7-wastes”-of-agile-software-deve
Important Terms and Concepts
http://www.scrumstudy.com/search.asp
Note: (from source)
If a requirement or design is never built because consumers don’t want it then the value of that inventory is zero. All of that investment was lost.
Increasing throughput
…through continuous improvement (Kaizen)
Identify the system’s bottle neck(s)
Decide how to exploit the bottlenecks.
Subordinate everything to the above decision (Make everything march to the “tune” of the bottleneck.
Elevate the system’s bottlenecks. (improve capacity at the bottleneck)
If in a previous step a bottleneck is broken, go back to step one. (system begins to breakdown)

## Operating Expenses - Operating
Operating Expenses*
Category | Salary | Benefits | Head Count | Cost Per Team Member | Total Compensation
Average Employees Developers | 97000 | 30361 | 5 | 127361 | 636805
Average Employees QA | 97000 | 30361 | 0 | 127361 | 0
Average Contractor Developers | 97000 |  | 3 | 97000 | 291000
Average Contractor QA | 83000 |  | 4 | 83000 | 332000
Average Contractor PM | 98000 |  | 1 | 98000 | 98000
Employee Benefits** | 31.3%
Salary Weeks*** | 50
Yearly Total | 472000 | 60722 | 13 | 532722 | 1357805
Weekly Total | 9440 | 1214.44 | 13 | 10654.44 | 27156.1
*Bases solely the average of various resource categories.
Sources:
**Total employer compensation costs for private industry workers taken from the Bureau of Labor Statistics 12/10/2104
http://www.bls.gov/news.release/ecec.nr0.htm
***Salary calculator
http://howmuchdoimakeayear.com/how-many-salary-weeks-in-a-year/